## Whitmore Park_NON BLM
Uinta Basin Railroad |  |  |  |  | Revisions by PJG 1/17/2019 per discussion with DLM:
Whitmore Park Corridor - NON BLM ROUTE |  |  |  |  | Cuts:
Structures List - RR Bridges |  |  |  |  | OX = | If greater than 24' cut (road over rail), install OH bridge (need total of 30' min for clear).
TO 6 - NEPA Engineering Support |  |  |  |  | At-grade = | If less than 24' cut (road over rail), at-grade xing if room to run out grade.
D.B. PJG-HDR 11/22/2019 |  |  |  |  | Fills:
[5 empty] | UX = | If greater than 15' fill (rail over road), install UP bridge (need total of 22' min for clear).
[5 empty] | At-grade = | If less than 15' fill (rail over road), at-grade xing if room to run out grade.
Railroad Bridges
Xing Station* | MP | Segment | Xing Type | Xing Name | No. Tracks | BR Type | BR Length (ft) [per track] | BR Height (ft) | Station Start** | TO 2 Notes PJG 6/25/2019 | TO 6 Notes PJG 11/22/2019
660 | 0.125 | Kyune Wye | Water | Price River | 1 | PCB | 300 | 8 | 510 | Over drainage next to UPRR. | No change to height or length, call TO 2 structure OK. | Shared w/ IC
4540 | 0.85985 | Kyune Wye | Water | Beaver Creek | 1 | PCB | 212 | 28 | 4434 | Over drainage. | Updated for stationing. | Unique to WP
6000 | 1.1364 | Kyune Wye | Water | Beaver Creek | 2 | DPG | 300 | 50 | 5850 | Over drainage. | Added bridge per GTK 11/8/2019. Base width of 100'. Cannot locate w/o stationing, estimated. Also, no profile specific to WP. | Unique to WP
6910 | 1.3087 | Kyune Wye | Water | Beaver Creek | 2 | DPG | 304 | 51 | 6758 | Over drainage. | Added bridge per GTK 11/8/2019. Base width of 100'. Cannot locate w/o stationing, estimated. Also, no profile specific to WP. | Unique to WP
7850 | 1.4867 | Main | Tracks & Water | UPRR (2 tracks) & Price River | 2 | DPG | 650 | 57-77-?? | 7295 | Raise over UPRR tracks. Bridge lengthened from 271' in UDOT study. | Increased length to span over UBRR loop track. Don't have Kyune Wye profile to check UBRR track elevation under bridge. | Unique to WP
8610 | 1.6307 | Main | Water | Kyune Creek | 2 | DPG | 380 | 60 | 8470 |  | Increased height and length per profile change, and changed to DPG due to height. | Unique to WP
14970 | 2.8352 | Main | Road & Water |  | 2 | PCB | 295 | 39 | 14870 | Need to keep as a road underpass (GK indicated drainage very small). | Matched IC | Shared w/ IC
39040 | 7.3939 | Main | Road | Horse Creek Road | 1 | PCB | 200 | 19 | 38940 |  | Revised for crossing road only; drainage separate/small. | Unique to WP, through NON-BLM
73465 | 13.9138 | Main | Road | Hwy 191 | 1 | BMS | 200 | 22 | 73370 |  | Need to raise track slighly (20' fill to 22' fill). Revised start station slightly. | Unique to WP, through NON-BLM
74030 | 14.0208 | Main | Water | Willow Creek | 1 | DPG | 282 | 48 | 73889 |  | Changed to DPG per GTK 11/8/2019. Base width of 60'. | Unique to WP, through NON-BLM
75940 | 14.3826 | Main | Road |  | 1 | PCB | 224 | 34 | 75828 |  | Track is high above exist. road - install bridge. | Unique to WP
88615 | 16.7831 | Main | Water | Minnie Maud Creek | 2 | DPG | 202 | 43 | 88505 |  | Added bridge per GTK 11/8/2019. Base width of 30'. | Unique to WP
100135 | 18.965 | Main | Road | Minnie Maud Creek Road | 1 | SSPA | 300 | 60 | 100135 |  | Track is high above exist. road - install SSPA. | Unique to WP
103440 | 19.5909 | Main | Road | Minnie Maud Creek Road | 1 | SSPA | 380 | 79 | 103440 |  | Track is high above exist. road - install SSPA. | Unique to WP
123510 | 23.392 | Main | Road |  | 1 | DPG | 820 | 172 | 123100 |  | Updated to DPG bridge per DLM 11/20/2019. | Shared w/ IC
193100 | 36.572 | Main | Water | Indian Canyon Creek | 1 | PCB | 86 | 14 | 193057 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
216740 | 41.0492 | Main | Water | Indian Canyon Creek | 2 | PCB | 74 | 11 | 216703 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
242000 | 45.8333 | Main | Water | Indian Canyon Creek | 1 | PCB | 110 | 20 | 241945 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
247465 | 46.8684 | Main | Water | Indian Canyon Creek | 1 | PCB | 74 | 11 | 247428 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
260245 | 49.2888 | Main | Water | Indian Canyon Creek | 1 | PCB | 90 | 15 | 260200 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
263600 | 49.9242 | Main | Water | Indian Canyon Creek | 2 | PCB | 114 | 21 | 263543 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
271340 | 51.3902 | Main | Water | Indian Canyon Creek | 1 | PCB | 174 | 36 | 271253 | Added bridge for debris control per GK and DLM 5/30/2019. 30' bottom width. | Matched IC | Shared w/ IC
291170 | 55.1458 | Main | Road |  | 1 | PCB | 168 | 30 | 291086 |  | Not overlapping IC, updated for taller fill. | Unique to WP
296300 | 56.1174 | Main | Water |  | 1 | DPG | 238 | 52 | 296181 |  | Not overlapping IC, updated for taller fill. | Unique to WP
305460 | 57.8523 | Main | Water |  | 1 | DPG | 308 | 57 | 305306 |  | Added bridge per GTK 11/8/2019. Base width of 80'. Updated for taller fill. | Unique to WP
312325 | 59.1525 | Main | Road |  | 2 | PCB | 202 | 31 | 312224 |  | Added per PJG 11/7/2019. Updated for taller fill. | Unique to WP
337250 | 63.8731 | Main | Road | Sowers Canyon Road | 1 | BMS | 156 | 20 | 337172 | Paved, tall enough fill for UX bridge. | Matched IC | Shared w/ IC
338425 | 64.0956 | Main | Water | Antelope Creek | 1 | DPG | 380 | 40 | 338235 | Per GK 1/9/2019, use 200' +/- bottom width, add slopes. | Matched IC | Shared w/ IC
346550 | 65.6345 | Main | Road |  | 1 | PCB | 186 | 32 | 346457 | Track is high above exist. road - install bridge. | Matched IC | Shared w/ IC
357200 | 67.6515 | Main | Road |  | 1 | PCB | 185 | 18 | 357107.5 | Track is high above exist. road - install bridge. | Matched IC | Shared w/ IC
387470 | 73.3845 | Main | Road | 5880 W Road | 1 | PCB | 200 | 38 | 387370 | Tall fill, install bridge | Matched IC | Shared w/ IC
* crossing feature location (not necessarily center of structure) | [8 empty] | ** for bridges (PCB, BMS, DPG), this is the abutment at low station.
** for SSPA, this is the station at centerline of structure.
Span Types: | [5 empty] | T/R - T/Bench in front of abutment, 2:1 slope down from there
PCB | = Precast Prestressed Concrete Double Cell Box Beam Span |  |  |  |  | PCB: | 7 | (ft)
BMS | = Rolled Steel Beam Span w/ Steel Pan Deck |  |  |  |  | BMS: | 9 | (ft)
DPG | = Built-up Steel Girder Span w/ Steel Pan Deck |  |  |  |  | DPG: | 12 | (ft)
SSPA | = Structural Steel Plate Arch